## Tasks
S.No | Title | Description | Status | Priority | Progress | Start Date | Due Date | Dependency Task | Dependency Details | Dependency Status | Dependency Owner | Final Comments
1 | Cloud account & billing setup | Provision the production AWS organization, billing alerts, IAM root hardening, and cost-allocation tags for LMS, AI, and content workloads. | Pending | Critical | 0 | 6/1/2026 | 6/2/2026
2 | VPC, networking & DNS baseline | Design and deploy the production VPC across 3 AZs, public/private subnets, NAT, VPC endpoints, and Route 53 zones for lms.invensislearning.com and api.invensislearning.com. | Pending | Critical | 0 | 6/1/2026 | 6/2/2026 | Cloud account & billing setup | AWS org and IAM must exist before networking can be cut. | Pending | Mayank
3 | Domain registration & SSL certificates | Confirm ownership of lms.invensislearning.com subdomain, provision ACM certificates, wire CloudFront, and register wildcard cert for *.lms.invensislearning.com. | Pending | Critical | 0 | 6/2/2026 | 6/3/2026 | VPC, networking & DNS baseline | Need Route 53 zone live before issuing ACM certs. | Pending | Mayank
4 | Production PostgreSQL (RDS) cluster | Provision RDS PostgreSQL 16 multi-AZ with read replica, automated backups (35 days), PITR, parameter group tuning, and KMS encryption. | Pending | Critical | 0 | 6/2/2026 | 6/3/2026 | VPC, networking & DNS baseline | Database must sit inside the production private subnets. | Pending | Mayank
5 | Redis (ElastiCache) for sessions & cache | Provision ElastiCache Redis cluster mode for session store, rate-limit counters, readiness-score cache, and AI response cache. | Pending | High | 0 | 6/2/2026 | 6/3/2026 | VPC, networking & DNS baseline | Cluster lives in private subnets created by networking task. | Pending | Mayank
6 | Container platform (ECS Fargate) | Stand up ECS Fargate clusters for web, API, and worker services with auto-scaling policies, task roles, and service discovery. | Pending | Critical | 0 | 6/2/2026 | 6/4/2026 | VPC, networking & DNS baseline | Requires private subnets and security groups from networking baseline. | Pending | Mayank
7 | CDN, WAF & edge config | Configure CloudFront distributions for the LMS frontend, signed-URL delivery for course content, and AWS WAF rules (rate limit, OWASP CRS, geo). | Pending | High | 0 | 6/3/2026 | 6/4/2026 | Domain registration & SSL certificates | CloudFront needs ACM certs in us-east-1. | Pending | Mayank
8 | Object storage for course content & uploads | Provision S3 buckets for course media, learner uploads, certificate PDFs, and exam-proof artifacts with lifecycle, versioning, and SSE-KMS. | Pending | High | 0 | 6/2/2026 | 6/3/2026 | Cloud account & billing setup | Needs the production AWS org and KMS keys. | Pending | Mayank
9 | Secrets management (Secrets Manager / Parameter Store) | Centralize all credentials, third-party API keys (LLM, payments, email, awarding bodies) in Secrets Manager with rotation and least-privilege task roles. | Pending | Critical | 0 | 6/2/2026 | 6/3/2026 | Container platform (ECS Fargate) | Tasks need IAM roles wired to Secrets Manager. | Pending | Mayank
10 | CI/CD pipeline (GitHub Actions + CodeDeploy) | Build pipelines for monorepo: lint, typecheck, unit tests, container build, ECR push, blue/green deploy to ECS, smoke tests on dev/stage/prod. | Pending | Critical | 0 | 6/3/2026 | 6/4/2026 | Container platform (ECS Fargate) | Pipeline targets ECS services that must exist first. | Pending | Mayank
11 | Observability stack — logs, metrics, traces | Wire CloudWatch Logs, OpenTelemetry traces to Datadog/Grafana, structured JSON logging, app dashboards, and PagerDuty alerts for SLO breaches. | Pending | High | 0 | 6/3/2026 | 6/5/2026 | Container platform (ECS Fargate) | Need running services to emit telemetry into the stack. | Pending | Mayank
12 | Error tracking (Sentry) integration | Onboard frontend (Next.js) and backend services to Sentry with release tracking, source maps, and per-stage alert rules. | Pending | Medium | 0 | 6/4/2026 | 6/5/2026 | CI/CD pipeline (GitHub Actions + CodeDeploy) | Release tags must be emitted from CI. | Pending | Mayank
13 | Backup, DR runbook & restore drill | Document RPO/RTO targets, weekly restore drill of RDS snapshots into staging, S3 cross-region replication for critical buckets. | Pending | High | 0 | 6/4/2026 | 6/5/2026 | Production PostgreSQL (RDS) cluster | Backups depend on the prod RDS being live. | Pending | Mayank
14 | Data model — courses, packages, exam specs | Author Prisma/SQL schema for courses, packages (Bronze/Silver/Gold), feature flags per tier, exam specs (pass mark, time, format), awarding bodies, and family rules. | Pending | Critical | 0 | 6/3/2026 | 6/5/2026 | Production PostgreSQL (RDS) cluster | Schema lands on the prod DB cluster. | Pending | Mayank
15 | Data model — users, enrollments, state machine | Schema for users, enrollments (per course+tier), enrollment state (active/ready/voucher_redeemed/exam_scheduled/exam_taken/passed/failed/refunded/closed), audit trail. | Pending | Critical | 0 | 6/4/2026 | 6/6/2026 | Data model — courses, packages, exam specs | Enrollments depend on courses/packages tables. | Pending | Mayank
16 | Data model — content (cards, guides, glossary) | Schema for reference cards, study guides with TOC, glossary terms, syllabus topic clusters, cross-references; per-course inventory with tier tagging. | Pending | High | 0 | 6/4/2026 | 6/6/2026 | Data model — courses, packages, exam specs | Content is keyed to course+tier rows. | Pending | Mayank
17 | Data model — question bank & mock exams | Schema for questions (stem, options, correct, explanation, difficulty, topic cluster, syllabus ref), question sessions, mock exam papers, and per-attempt records. | Pending | High | 0 | 6/4/2026 | 6/6/2026 | Data model — content (cards, guides, glossary) | Reuses syllabus topic clusters defined in content schema. | Pending | Mayank
18 | Data model — readiness, voucher, money-back | Schema for readiness inputs (mock attempts, qbank coverage, gap-report ack), voucher inventory, awarding-body bindings, override audit, money-back claims. | Pending | Critical | 0 | 6/5/2026 | 6/7/2026 | Data model — users, enrollments, state machine | Voucher/readiness lives on the enrollment state machine. | Pending | Mayank
19 | Data model — live services, cashback, support | Schema for live sessions, RSVPs, coaching credits, support tickets, cashback ledger entries, attendance records, certificates. | Pending | High | 0 | 6/5/2026 | 6/7/2026 | Data model — users, enrollments, state machine | All Stage 5 entitlements hang off enrollments. | Pending | Mayank
20 | Migration framework & seed data | Standardize Prisma migrations, write seed data for 3 reference courses (PMP, PRINCE2 F, PRINCE2 P) across all three tiers for dev/stage. | Pending | Medium | 0 | 6/6/2026 | 6/7/2026 | Data model — question bank & mock exams | Seeds require all schema parts to exist. | Pending | Mayank
21 | Authentication service (NextAuth + JWT) | Email/password auth, refresh tokens, session rotation, secure cookie config, MFA scaffolding for staff accounts. | Pending | Critical | 0 | 6/5/2026 | 6/7/2026 | Data model — users, enrollments, state machine | Auth keys off the users table. | Pending | Mayank
22 | Activation token flow | One-time activation tokens issued from the welcome email, expiry, regeneration on expired link (Stage 2 side flow), audit logging. | Pending | Critical | 0 | 6/6/2026 | 6/7/2026 | Authentication service (NextAuth + JWT) | Builds on the auth primitives. | Pending | Mayank
23 | Password reset & forgot-password | Forgot-password email, reset-token verification, password strength rules, brute-force throttling via Redis. | Pending | High | 0 | 6/6/2026 | 6/8/2026 | Authentication service (NextAuth + JWT) | Reuses the auth + email infra. | Pending | Mayank
24 | Role-based access control (learner/instructor/ops/admin) | Authorization layer with RBAC for learner, instructor, ops, finance, content-author, and admin roles; per-route guards on the API. | Pending | High | 0 | 6/7/2026 | 6/9/2026 | Authentication service (NextAuth + JWT) | Roles attach to users. | Pending | Mayank
25 | Transactional email service (SES + templates) | SES production sending domain, DKIM/SPF/DMARC, MJML templates for welcome, activation, reset, receipts, nudges. Bounce + complaint handling. | Pending | Critical | 0 | 6/5/2026 | 6/7/2026 | Domain registration & SSL certificates | DKIM records live on the LMS DNS zone. | Pending | Mayank
26 | Order ingestion API from invensislearning.com | Webhook + signed API for invensislearning.com to push paid orders (buyer email, course slug, tier, amount, order ref) into the LMS, idempotent. | Pending | Critical | 0 | 6/7/2026 | 6/9/2026 | Data model — users, enrollments, state machine | Creates a user + enrollment on receipt. | Pending | Mayank
27 | LMS welcome email & activation landing | Welcome email triggered on enrollment creation; activation landing page /activate/[token] with course/tier hero card pulled from catalogue. | Pending | Critical | 0 | 6/8/2026 | 6/10/2026 | Activation token flow | Wires email button to the token endpoint. | Pending | Mayank
28 | Set-password & T&C acceptance screen | /auth/activate flow with email locked, password strength, T&C checkbox, audit log of acceptance with version + timestamp. | Pending | High | 0 | 6/9/2026 | 6/10/2026 | LMS welcome email & activation landing | Continues the activation flow. | Pending | Mayank
29 | Onboarding wizard — profile, exam date, baseline | Four-step onboarding (/onboarding/[id]/...) — profile capture, exam-date picker with countdown, 20-Q baseline runner, completion page. | Pending | High | 0 | 6/9/2026 | 6/11/2026 | Set-password & T&C acceptance screen | Onboarding starts after activation. | Pending | Mayank
30 | LMS dashboard shell — tier-scoped tiles | Dashboard /lms/[slug] rendering tier-scoped sections (Core, Exam Prep, AI, Active Learning, Support), status banner (exam date, progress, readiness, voucher), locked-tile upgrade CTAs. | Pending | Critical | 0 | 6/10/2026 | 6/12/2026 | Onboarding wizard — profile, exam date, baseline | Dashboard is what onboarding hands off to. | Pending | Mayank
31 | Reference card viewer engine | Generic card viewer /lms/[slug]/reference/[card] with left nav, prev/next, mark-as-read, bookmark, reading progress per learner. | Pending | High | 0 | 6/10/2026 | 6/12/2026 | Data model — content (cards, guides, glossary) | Renders rows from the content schema. | Pending | Mayank
32 | Study guide viewer with TOC & scroll progress | Longer-form guide viewer /lms/[slug]/study-guide/[guide] with sticky TOC, anchor jumps, scroll progress, bookmark. | Pending | Medium | 0 | 6/10/2026 | 6/12/2026 | Reference card viewer engine | Shares chrome/components. | Pending | Mayank
33 | Searchable glossary | /lms/[slug]/glossary with A–Z index, full-text search across terms + definitions, cross-references back to cards/guides. | Pending | Medium | 0 | 6/11/2026 | 6/12/2026 | Data model — content (cards, guides, glossary) | Indexes glossary rows. | Pending | Mayank
34 | Question bank engine — topic picker + runner | Topic-clustered picker with difficulty/wrong-only filters, session lengths (10/25/50), runner with explanation reveal, session results with per-topic breakdown. | Pending | Critical | 0 | 6/11/2026 | 6/14/2026 | Data model — question bank & mock exams | Engine reads question rows. | Pending | Mayank
35 | Mock exam runner — closed-book | Timed mock runner /lms/[slug]/mock-exam/[id]/run with sticky timer, question navigator, flag, auto-save, submit confirmation modal (unanswered + flagged + remaining time). | Pending | Critical | 0 | 6/12/2026 | 6/15/2026 | Question bank engine — topic picker + runner | Reuses question rendering and per-attempt records. | Pending | Mayank
36 | Mock exam runner — open-book variant | Scenario block + collapsible manual sidebar for Practitioner-level open-book papers; format driven by course examSpecs (Variation A in plan). | Pending | High | 0 | 6/13/2026 | 6/15/2026 | Mock exam runner — closed-book | Builds on the closed-book runner; format flips per paper. | Pending | Mayank
37 | Mock exam results & readiness refresh | /result page with pass/fail vs course pass mark, per-topic chart, full question review, AI gap-report CTA (Silver/Gold), readiness-score update. | Pending | Critical | 0 | 6/13/2026 | 6/15/2026 | Mock exam runner — closed-book | Results read from per-attempt records. | Pending | Mayank
38 | Combo course dual sub-section dashboard | Render Foundation and Practitioner sub-sections, two voucher tiles, two readiness targets for F+P combos per Variation B. | Pending | Medium | 0 | 6/14/2026 | 6/16/2026 | LMS dashboard shell — tier-scoped tiles | Extends the base dashboard with dual-level groupings. | Pending | Mayank
39 | LLM provider integration & abstraction | Provider abstraction over Anthropic Claude (primary) and OpenAI (fallback), streaming, retries, structured-output parsing, prompt template registry. | Pending | Critical | 0 | 6/13/2026 | 6/15/2026 | Secrets management (Secrets Manager / Parameter Store) | API keys live in secrets. | Pending | Mayank
40 | Vector store & syllabus RAG index | Per-course vector index (pgvector) of reference cards, guides, glossary, syllabus refs; ingestion pipeline keyed to content edits; refusal layer reads boundary from index. | Pending | Critical | 0 | 6/13/2026 | 6/16/2026 | Data model — content (cards, guides, glossary) | Indexes content rows. | Pending | Mayank
41 | AI study plan generator (Silver templated / Gold personalised) | Day-by-day plan to exam date; Silver picks one of three templated cadences; Gold re-generates from latest mock + baseline + profile. Diff + confirm on regenerate. | Pending | High | 0 | 6/14/2026 | 6/17/2026 | LLM provider integration & abstraction | Calls LLM for personalised plan; deterministic for templated. | Pending | Mayank
42 | AI gap report after mock attempt | From last mock attempt: topic-cluster strengths chart, 3–5 prioritised deep-linked actions, plain-language narrative. Ack state feeds readiness gate. | Pending | High | 0 | 6/14/2026 | 6/17/2026 | Mock exam results & readiness refresh | Consumes mock attempt records. | Pending | Mayank
43 | Adaptive flashcards (SM-2 / FSRS) | Card scheduler, per-learner recall history, Drill Mode (Gold) prioritising weak-area cards from latest gap report. | Pending | Medium | 0 | 6/15/2026 | 6/18/2026 | AI gap report after mock attempt | Drill Mode reads gap-report weak areas. | Pending | Mayank
44 | AI concept coach (Gold) with citations + refusal | Chat surface /ai/concept-coach with grounded answers + citation links into Stage 3 content; out-of-syllabus refusal with 3 in-scope suggestions; fair-use cap. | Pending | High | 0 | 6/15/2026 | 6/18/2026 | Vector store & syllabus RAG index | Retrieval-grounded against per-course index. | Pending | Mayank
45 | AI scenario coach (Gold, Practitioner-only) | Branching scenario dialogue, 4–6 turns, rubric-scored summary. Tile not rendered on Foundation courses per Trap #7. | Pending | Medium | 0 | 6/16/2026 | 6/18/2026 | AI concept coach (Gold) with citations + refusal | Shares chat infra and rate limits. | Pending | Mayank
46 | AI interview coach (Gold, in Support) | Role picker → 5–10 mock interview questions → per-answer feedback (clarity, structure, STAR). Lives under Support & Mentoring, not Exam Prep. | Pending | Low | 0 | 6/17/2026 | 6/19/2026 | AI concept coach (Gold) with citations + refusal | Reuses chat surface. | Pending | Mayank
47 | Daily AI challenge (Gold, cohort-wide) | One scenario per calendar date, same for the whole cohort; reveal-model-answer; optional comments; archive with date locks. | Pending | Low | 0 | 6/17/2026 | 6/19/2026 | LLM provider integration & abstraction | Generates daily scenarios from rotating syllabus. | Pending | Mayank
48 | AI cost cap, rate limiting & abuse controls | Per-learner daily message cap on coaches, quiet rate-limit UX (no upsell), per-org spend budget alarms, prompt-injection guardrails. | Pending | High | 0 | 6/17/2026 | 6/19/2026 | AI concept coach (Gold) with citations + refusal | Caps the chat surfaces. | Pending | Mayank
49 | Live training schedule & RSVP | Calendar of session blocks with timezone conversion, instructor + capacity + RSVP state, post-session recording link within 24h. | Pending | High | 0 | 6/14/2026 | 6/17/2026 | Data model — live services, cashback, support | Renders scheduled sessions. | Pending | Mayank
50 | Zoom/Teams meeting bridge | Auto-provision Zoom meetings per session block, push join-links to learners, store recordings to S3 with signed-URL access. | Pending | High | 0 | 6/15/2026 | 6/18/2026 | Live training schedule & RSVP | Schedule must exist to provision meetings. | Pending | Mayank
51 | Q&A session booking | Recurring weekly/twice-weekly Q&A slots with RSVP, instructor on duty, attendance count. | Pending | Medium | 0 | 6/16/2026 | 6/18/2026 | Live training schedule & RSVP | Shares the scheduling component. | Pending | Mayank
52 | 1:1 coaching booking (Gold) | Coach availability, credit ledger (Standalone Gold = 3 flex; Combo Gold = F→P→flex sequencing), pre-call prep, cancellation window (12h forfeit rule). | Pending | High | 0 | 6/17/2026 | 6/19/2026 | Live training schedule & RSVP | Coaches share the scheduling primitives. | Pending | Mayank
53 | Support ticketing (email + chat + phone) | Inbox /lms/[slug]/support, ticket threads with attachments, status, tier-scoped channel availability, phone-call button when Gold + agent online. | Pending | High | 0 | 6/17/2026 | 6/19/2026 | Role-based access control (learner/instructor/ops/admin) | Ops/agents need RBAC roles. | Pending | Mayank
54 | Live chat widget integration | Intercom/Crisp widget on the LMS, scoped to learner identity, tier-aware availability hints, agent routing by course family. | Pending | Medium | 0 | 6/17/2026 | 6/19/2026 | Support ticketing (email + chat + phone) | Chat threads roll up into the ticketing system. | Pending | Mayank
55 | Phone-support routing (Gold) | Click-to-call from ticket thread when agent online; Twilio/Exotel bridge; call recording + transcript attached to ticket. | Pending | Medium | 0 | 6/18/2026 | 6/20/2026 | Support ticketing (email + chat + phone) | Calls are anchored to a ticket. | Pending | Mayank
56 | Community access (Discord/Circle) | /lms/[slug]/community landing, code-of-conduct gate, automated invite to per-course Discord channel scoped by enrollment. | Pending | Low | 0 | 6/18/2026 | 6/20/2026 | Role-based access control (learner/instructor/ops/admin) | Invite gated by enrollment. | Pending | Mayank
57 | Cashback ledger & payout request | Accrual events (enrolment %, session attendance, mock completion), tier-aware percentages (5/8/12), payout request once over threshold, bank/UPI capture. | Pending | Medium | 0 | 6/19/2026 | 6/21/2026 | Data model — live services, cashback, support | Writes against the ledger schema. | Pending | Mayank
58 | Attendance certificate generator | Auto-issue downloadable PDF at ≥80% live-session attendance; LinkedIn share helper; not the final certification. | Pending | Medium | 0 | 6/19/2026 | 6/21/2026 | Live training schedule & RSVP | Requires attendance records from the schedule. | Pending | Mayank
59 | Money-back guarantee panel (Gold visibility) | Always-visible /money-back panel with plain-language terms, gate-progress checklist mirror, claim CTA greyed out until a recorded fail; combo learners see 'either exam' qualifier. | Pending | High | 0 | 6/20/2026 | 6/21/2026 | Data model — readiness, voucher, money-back | Reads the gate-honoured audit data. | Pending | Mayank
60 | Readiness score engine | Computes composite 0–100 from mock attempts (tier threshold), Q-bank coverage (≥70% with no cluster <50%), and gap-report acks (Silver≥1 / Gold≥2). Tier-specific weights. | Pending | Critical | 0 | 6/17/2026 | 6/20/2026 | Mock exam results & readiness refresh | Inputs come from Stage 3 + Stage 4. | Pending | Mayank
61 | Enrollment state machine & audit trail | active → ready → voucher_redeemed → exam_scheduled → exam_taken → (passed¦failed) → (closed¦refunded). Every transition logged with actor, inputs, and reason. | Pending | Critical | 0 | 6/17/2026 | 6/20/2026 | Readiness score engine | Auto-transitions when gate crosses. | Pending | Mayank
62 | Voucher inventory & assignment | Per-awarding-body pools, allocation on redeem, expiry tracking (12-month TTL warning), idempotency for retries. | Pending | Critical | 0 | 6/18/2026 | 6/20/2026 | Enrollment state machine & audit trail | Redeem event consumes a voucher. | Pending | Mayank
63 | Readiness panel & drill-downs UI | /readiness with composite, three input cards, projected ready-by date, drill into mocks/qbank/gap-reports with deep-links into Stage 3/4. | Pending | High | 0 | 6/18/2026 | 6/21/2026 | Readiness score engine | Reads from the score engine. | Pending | Mayank
64 | Voucher tile, reveal modal & booking handoff | Locked → unlocked tile transitions, reveal modal with code + body branding + TTL + copy, handoff page linking to awarding-body booking portal. | Pending | High | 0 | 6/19/2026 | 6/21/2026 | Voucher inventory & assignment | Renders an allocated voucher row. | Pending | Mayank
65 | Early-redeem override flow | Hard-confirm modal that explicitly forfeits the Gold money-back guarantee; logged in audit with reason; reflected in claim eligibility check. | Pending | Medium | 0 | 6/20/2026 | 6/22/2026 | Voucher tile, reveal modal & booking handoff | Overrides the gate before reveal. | Pending | Mayank
66 | Awarding-body integrations (PeopleCert, PMI, APMG) | Initial integrations for PeopleCert (PRINCE2/ITIL), PMI/Prometric (PMP family), APMG (Change Mgmt); result webhook ingestion where supported. | Pending | High | 0 | 6/19/2026 | 6/22/2026 | Voucher inventory & assignment | Webhooks update enrollment state. | Pending | Mayank
67 | Exam day prep & standby screens | Countdown + checklist on /exam-day; auto-routed /exam-day/active during booked window with study tools disabled. | Pending | Medium | 0 | 6/20/2026 | 6/21/2026 | Voucher tile, reveal modal & booking handoff | Triggered by scheduled state. | Pending | Mayank
68 | Outcome recording (webhook + manual) | Webhook ingest from awarding bodies where supported; manual form with proof upload for the rest; ops verify gate for Silver/Gold flips. | Pending | Critical | 0 | 6/20/2026 | 6/22/2026 | Awarding-body integrations (PeopleCert, PMI, APMG) | Webhook flows in via the body integration. | Pending | Mayank
69 | Certificate page & PDF generation | Mirror awarding-body certificate with downloadable PDF, verifiable URL, distinction badge when applicable. | Pending | High | 0 | 6/21/2026 | 6/22/2026 | Outcome recording (webhook + manual) | Issued after pass is recorded. | Pending | Mayank
70 | Pass — social share & post-cert pathways | LinkedIn/X/WhatsApp pre-filled cards with referral attribution back to invensislearning.com; curated pathway list (Foundation→Practitioner, PMP→PgMP, etc.). | Pending | Medium | 0 | 6/21/2026 | 6/23/2026 | Certificate page & PDF generation | Surfaces after certificate page. | Pending | Mayank
71 | Renewal tracker (PDU + re-registration) | PMP PDU tracker (60 PDU / 3 yr, Talent Triangle categories); PRINCE2 Practitioner 3-yr re-reg countdown; ITIL 4 renewal countdown; lifetime certs hide section. | Pending | Medium | 0 | 6/22/2026 | 6/23/2026 | Certificate page & PDF generation | Activated post-pass per cert renewal policy. | Pending | Mayank
72 | Fail outcome view & recovery paths | Tier-aware recovery: Bronze re-purchase, Silver retake (1×90d), Gold retake (2×180d) + money-back claim; gentle messaging. | Pending | High | 0 | 6/21/2026 | 6/23/2026 | Outcome recording (webhook + manual) | Branches on recorded failure. | Pending | Mayank
73 | Retake training booking | Re-attend live sessions, credit ledger, post-retake re-opening of the readiness gate. | Pending | Medium | 0 | 6/22/2026 | 6/23/2026 | Fail outcome view & recovery paths | Branches off the fail view. | Pending | Mayank
74 | Money-back claim form & verification | Pre-populated claim with gate-honoured checklist (mock, qbank, gap-report ack at redemption), bank/UPI pre-fill, override rejection logic. | Pending | Critical | 0 | 6/22/2026 | 6/23/2026 | Fail outcome view & recovery paths | Claim is gated on the fail outcome. | Pending | Mayank
75 | Refund request relay to invensislearning.com | LMS does not own the payment gateway. On approved money-back claim, the LMS sends a signed refund request to invensislearning.com (which owns Razorpay/Stripe), polls/receives a status webhook, and surfaces the timeline (submitted/verified/approved/rejected/refunded) to the learner. | Pending | High | 0 | 6/22/2026 | 6/24/2026 | Money-back claim form & verification | Triggered on approved claim. | Pending | Mayank
76 | Catalogue authoring admin (courses & packages) | Admin UI to create/edit courses, three packages per course, feature inclusion matrix, exam specs, awarding-body binding. | Pending | High | 0 | 6/13/2026 | 6/16/2026 | Data model — courses, packages, exam specs | Edits the catalogue schema. | Pending | Mayank
77 | Content authoring admin (cards, guides, glossary) | Markdown/MDX editor for reference cards and study guides, glossary CRUD, syllabus mapping, per-tier visibility, draft/publish workflow. | Pending | High | 0 | 6/14/2026 | 6/18/2026 | Data model — content (cards, guides, glossary) | CRUD on content rows. | Pending | Mayank
78 | Question bank authoring admin | Bulk import (CSV), per-question editor (stem, options, explanation, topic cluster, difficulty, syllabus ref), validation, mock-paper composer. | Pending | High | 0 | 6/17/2026 | 6/20/2026 | Data model — question bank & mock exams | CRUD on questions and papers. | Pending | Mayank
79 | Instructor & coach admin | Instructor profiles, bios, qualifications, ratings, schedule assignment to live training and coaching slots. | Pending | Medium | 0 | 6/17/2026 | 6/19/2026 | Live training schedule & RSVP | Schedule references instructors. | Pending | Mayank
80 | Ops console — enrollments, vouchers, claims | Search enrollments by user/order, force-transition state (with audit reason), allocate/recall vouchers, review money-back claims. | Pending | High | 0 | 6/18/2026 | 6/21/2026 | Enrollment state machine & audit trail | Reads and writes against the state machine. | Pending | Mayank
81 | Analytics dashboards (BI) | Cohort funnels (activation→onboarding→first mock→ready→redeem→pass), per-course pass rates, AI usage, support load, cashback liability. | Pending | Medium | 0 | 6/19/2026 | 6/23/2026 | Observability stack — logs, metrics, traces | Reuses telemetry pipeline + warehouse. | Pending | Mayank
82 | Privacy, GDPR & DPDP compliance | Data inventory, lawful-basis register, learner rights flows (export, delete, rectify), DPA templates with vendors (LLM, payments, email). | Pending | High | 0 | 6/13/2026 | 6/18/2026 | Data model — users, enrollments, state machine | Maps lawful basis to user data. | Pending | Mayank
83 | Terms of service, refund policy & cookie consent | Legal copy reviewed for India + EU + UK + US, versioned acceptance log, cookie consent banner with category controls. | Pending | Medium | 0 | 6/14/2026 | 6/18/2026 | Set-password & T&C acceptance screen | Versions tied to acceptance logs. | Pending | Mayank
84 | Security baseline & pen test | OWASP top-10 baseline review, dependency scanning, container CVE scans, third-party pen test, remediation pass. | Pending | Critical | 0 | 6/18/2026 | 6/23/2026 | CI/CD pipeline (GitHub Actions + CodeDeploy) | Scans run in the pipeline. | Pending | Mayank
85 | Accessibility audit (WCAG 2.2 AA) | Automated + manual audit across all learner screens, fix queue, keyboard nav, screen-reader labels, color-contrast pass. | Pending | Medium | 0 | 6/19/2026 | 6/23/2026 | LMS dashboard shell — tier-scoped tiles | Audit covers the live dashboard surfaces. | Pending | Mayank
86 | Unit & integration test coverage baseline | Vitest/Jest unit coverage targets (engines, scoring, state machine), Supertest for API, ≥70% line coverage on critical packages. | Pending | High | 0 | 6/17/2026 | 6/22/2026 | Question bank engine — topic picker + runner | Tests trail behind the engines. | Pending | Mayank
87 | E2E test suite (Playwright) | End-to-end tests for the 7-stage golden path per tier (Bronze/Silver/Gold), combo course, fail+refund branch. | Pending | High | 0 | 6/19/2026 | 6/24/2026 | Money-back claim form & verification | Covers the full journey including the refund branch. | Pending | Mayank
88 | Load & soak testing | k6 scenarios for mock-exam start spikes, AI coach concurrency, dashboard reads; identify and tune bottlenecks. | Pending | Medium | 0 | 6/22/2026 | 6/24/2026 | Observability stack — logs, metrics, traces | Reads metrics during runs. | Pending | Mayank
89 | UAT with internal cohort & beta learners | Closed UAT with 30 internal users and 50 external beta learners across PMP / PRINCE2 F / PRINCE2 P, all three tiers, bug triage. | Pending | Critical | 0 | 6/23/2026 | 6/25/2026 | E2E test suite (Playwright) | UAT starts after the suite is green. | Pending | Mayank
90 | Migration of historical learners (if any) | ETL of any existing invensislearning.com learner data and active enrollments into the new LMS with state mapped to the new state machine. | Pending | Medium | 0 | 6/24/2026 | 6/25/2026 | Enrollment state machine & audit trail | Maps legacy state into the new machine. | Pending | Mayank
91 | SEO, schema markup & sitemap | Sitemap, robots.txt, JSON-LD course schema on public pages, canonicals, OG tags for share cards. | Pending | Low | 0 | 6/24/2026 | 6/25/2026 | Certificate page & PDF generation | Share cards link to public surfaces. | Pending | Mayank
92 | Production go-live & launch runbook | Cutover plan, freeze window, smoke test plan, rollback plan, status page, on-call schedule for launch + first 14 days. | Pending | Critical | 0 | 6/25/2026 | 6/26/2026 | UAT with internal cohort & beta learners | Go-live conditioned on UAT sign-off. | Pending | Mayank
93 | Post-launch hypercare & SLO review | Two-week hypercare with daily standup, defect burn-down, SLO dashboards, paging tuning, and a 30-day retro. | Pending | High | 0 | 6/26/2026 | 6/30/2026 | Production go-live & launch runbook | Starts the moment the system is live. | Pending | Mayank

## Instructions
BULK TASK UPLOAD — HOW TO USE THIS TEMPLATE
1. Open the "Tasks" sheet (first tab).
2. Replace the sample rows with your own. Keep the header row in row 1 unchanged.
3. Save the file as .xlsx (or export to .csv) and upload via "Bulk Upload Tasks" in the project page.
IMPORTANT
• Only the "Title" column is required. Every other column is optional.
• Dates can be MM/DD/YYYY (US) or YYYY-MM-DD. Excel date cells are also accepted.
• Progress must be a whole number between 0 and 100.
• If a row has any Dependency fields filled, "Dependency Task" must be set.
• "Dependency Owner" accepts an active user's full name OR a comma-separated list of names. See the Reference tab for the full list.
• Empty rows are skipped. Rows missing the Title will be flagged in the preview.
INSTRUCTIONS PER COLUMN
Field | Required? | What to enter | If left blank
A. Title | Yes | A short task name (preferably under 80 chars). This is how the row appears in the upload preview. | Row is skipped and shown as invalid in the preview.
B. Description | No | Free-text details / context. Newlines are preserved. | No description on the imported task.
C. Status | No | One of: Pending / In Progress / Completed (see Reference tab for synonyms). | Defaults to Pending.
D. Priority | No | One of: Low / Medium / High / Critical. | Defaults to Medium.
E. Progress | No | Whole number 0 to 100. | Treated as 0. Auto-set to 100 if Status = Completed.
F. Start Date | No | When work begins. MM/DD/YYYY or YYYY-MM-DD or an Excel date cell. | No start date set.
G. Due Date | No (rec.) | Deadline. Same date formats as Start Date. Recommended for reporting. | Task is un-dated; reports treat it as having no deadline.
H. Dependency Task | See note | Name of the upstream/blocking task. Required if ANY of I, J, or K below is filled. | No dependency recorded on the task.
I. Dependency Details | No | Why the dependency blocks. Free-text. Only meaningful if H is set. | No detail; the dependency exists but with no extra context.
J. Dependency Status | No | One of: Pending / In Progress / In Review / Completed / Blocked. | Defaults to Pending. Only meaningful if H is set.
K. Dependency Owner | No | Full name(s) of an active user. Single name or comma-separated for joint ownership. See Reference tab for the live list of valid names. | No owner attached. Unmatched names are flagged in the preview.
L. Final Comments | No | Wrap-up note added when the task closes. Often filled in when Status = Completed. | No closing note on the imported task.
NEED MORE DETAIL?
• The "Reference" tab lists every accepted value, synonym, and example for each column.
• Need a plaintext version? Use the "CSV" template from the same modal — same columns, no extra tabs.

## Reference
REFERENCE — Accepted values and examples for every column
Use this tab when filling in the Tasks sheet. Sections appear in the same column order.
─── A. TITLE (required, free text) ───
Guidance | Notes
Short | Aim for under 80 characters. Title is the row identifier in the preview.
Action verb | Start with a verb where natural — "Build homepage hero", "Refactor login flow".
Unique | Two rows can share a title, but unique titles make dependencies easier to reference.
Examples
Header design
Homepage hero animation
SEO audit fixes
─── B. DESCRIPTION (optional, free text) ───
Guidance | Notes
Multi-line | Newlines are preserved on import. Use them for sub-bullets or context.
Length | No hard cap, but the preview truncates very long values for readability.
Examples
Build the responsive site header with sticky navigation
Move all forms to react-hook-form + zod
─── C. STATUS (optional enum, defaults to "Pending") ───
Value | Notes / Synonyms accepted on import
Pending | Default. Synonyms: Not Started, To Do, Open, Backlog.
In Progress | Work is underway. Synonyms: WIP, In-Progress, Working, Doing.
Completed | Done. Synonyms: Done, Closed, Finished, Shipped.
─── D. PRIORITY (optional enum, defaults to "Medium") ───
Value | Notes
Low | Nice-to-have / low impact.
Medium | Default if left blank.
High | Important and time-sensitive.
Critical | Highest urgency — blocks releases or revenue.
─── E. PROGRESS (optional integer, 0–100) ───
Value | Notes
0 | Not started. Use with Status = Pending.
1 to 99 | In flight. Whole numbers only. Decimals are rounded down.
100 | Fully done. Auto-set if Status = Completed and Progress is blank.
Blank | Treated as 0.
─── F. START DATE (optional, date) ───
Format | Example
US slash | 6/15/2026
ISO | 2026-06-15
Excel date cell | Any cell formatted as a date in Excel works.
Blank | No start date set — the task can begin immediately.
Rule | Must be on or before Due Date if both are set.
─── G. DUE DATE (optional, date — recommended) ───
Format | Example
US slash | 6/30/2026
ISO | 2026-06-30
Excel date cell | Any cell formatted as a date in Excel works.
Blank | No deadline shown on the task row. Reporting will treat it as un-dated.
─── H. DEPENDENCY TASK (optional, free text) ───
Guidance | Notes
Format | Plain task name. Doesn't need to exactly match another row's Title.
When to use | Whenever this task is blocked or waiting on another piece of work.
Rule | If ANY of columns I, J, or K is filled, column H must also be filled.
Examples
Brand guidelines sign-off
API error contract
Hero copy approval
─── I. DEPENDENCY DETAILS (optional, free text) ───
Guidance | Notes
Purpose | Explain what you're waiting for and why it blocks.
Examples
Need final logo + colour tokens before final pass
Backend needs to standardise validation error payload
Awaiting final hero copy from content team
─── J. DEPENDENCY STATUS (optional enum) ───
Value | Notes
Pending | Hasn't started.
In Progress | Owner is working on it.
In Review | Awaiting review/sign-off.
Completed | Done — no longer blocking.
Blocked | The dependency itself is blocked.
─── K. DEPENDENCY OWNER (optional, matches an active user's full name) ───
Format | Notes
Single | One active user's full name — e.g. "Kiran R".
Multiple | Comma-separated for joint ownership — e.g. "Kiran R, Lokesh".
Match rule | Case-insensitive. Exact match preferred; startsWith and contains are used as fallbacks.
Unmatched | Names that don't match any active user are flagged in the preview so you can fix them before importing.
Active user names — accepted values
# | Full name
1 | Kiran R
2 | Lokesh
3 | Mayank
4 | NagaPrasanth
5 | Nageswara Rao
6 | Ranjith Kumar
7 | Somashekara
8 | Spandana HR
9 | Surya L
10 | Vaibhav
11 | Vamsi Krishna
12 | Venkataramana
13 | Vijay
14 | Vijay 2
15 | Vimala Nayuni
Tip | This list is generated live from the database at download time. Re-download the template if a new member joins.
─── L. FINAL COMMENTS (optional, free text) ───
Guidance | Notes
When to use | Wrap-up note. Often filled in when Status = Completed.
Examples
Done — all audit items addressed.
Awaiting brand sign-off; once approved, can wrap in a day.
Frontend pieces done; integration paused on backend contract.