## Tasks
S.No | Title | Description | Status | Priority | Progress | Start Date | Due Date | Dependency Task | Dependency Details | Dependency Status | Dependency Owner | Final Comments
1 | Activation landing page UI | Renders /activate/[token] with course + tier hero card and a single CTA. Stage 2 screen 2. | Completed | Medium | 100 | 5/1/2026 | 5/22/2026 |  |  |  |  | Prototype shipped at /app/activate/[token]/page.tsx.
2 | Set-password & T&C UI | /auth/activate screen with email locked, new password + confirm, strength hints, T&C checkbox. Stage 2 screen 3. | Completed | Medium | 100 | 5/1/2026 | 5/22/2026 |  |  |  |  | Prototype shipped at /app/auth/activate/page.tsx.
3 | Return login UI | /auth/login with email + password and forgot-password link. Stage 2 side flow. | Completed | Medium | 100 | 5/1/2026 | 5/22/2026 |  |  |  |  | Prototype shipped at /app/auth/login/page.tsx.
4 | Forgot-password request UI | /auth/forgot-password with email field and 'Send reset link' CTA. Stage 2 side flow. | Completed | Medium | 100 | 5/1/2026 | 5/22/2026 |  |  |  |  | Prototype shipped at /app/auth/forgot-password/page.tsx.
5 | Forgot-password sent confirmation UI | /auth/forgot-password/sent confirmation screen prompting the learner to check their inbox. | Completed | Medium | 100 | 5/1/2026 | 5/22/2026 |  |  |  |  | Prototype shipped at /app/auth/forgot-password/sent/page.tsx.
6 | Reset password UI | /auth/reset-password/[token] with new password + confirm and success state. Stage 2 side flow. | Completed | Medium | 100 | 5/1/2026 | 5/22/2026 |  |  |  |  | Prototype shipped at /app/auth/reset-password/[token]/page.tsx.
7 | Onboarding welcome UI | Single-course welcome screen with four-step indicator (Profile → Exam date → Baseline → Done) and Get-started CTA. Stage 2 screen 4. | Completed | Medium | 100 | 5/1/2026 | 5/22/2026 |  |  |  |  | Prototype shipped at /app/welcome/page.tsx.
8 | Onboarding welcome — multi-enrollment UI | Variant welcome surface for learners with multiple enrollments. | Completed | Medium | 100 | 5/1/2026 | 5/22/2026 |  |  |  |  | Prototype shipped at /app/welcome-multi/page.tsx.
9 | Profile capture UI | Step 1: role, years of experience, domain background, study hours, English proficiency, progress bar. Stage 2 screen 5. | Completed | Medium | 100 | 5/1/2026 | 5/22/2026 |  |  |  |  | Prototype shipped at /app/onboarding/profile/page.tsx.
10 | Exam target date UI | Step 2: date picker, countdown to exam, recommended study cadence. Stage 2 screen 6. | Completed | Medium | 100 | 5/1/2026 | 5/22/2026 |  |  |  |  | Prototype shipped at /app/onboarding/exam-date/page.tsx.
11 | Baseline mock UI | Step 3: 20-question baseline intro, timed mini-mock, results breakdown by topic cluster. Stage 2 screen 7. | Completed | Medium | 100 | 5/1/2026 | 5/22/2026 |  |  |  |  | Prototype shipped at /app/onboarding/baseline/page.tsx.
12 | Onboarding complete UI | Step 4: 'You're ready' confirmation with faded dashboard preview behind. Stage 2 screen 8. | Completed | Medium | 100 | 5/1/2026 | 5/22/2026 |  |  |  |  | Prototype shipped at /app/onboarding/complete/page.tsx.
13 | LMS course dashboard shell UI | Per-course dashboard /lms/[slug] with section groupings (Core training, Exam Preparation, Active Learning, Support). Stage 2 screen 9 + Stage 3 screen 1. | Completed | Medium | 100 | 5/1/2026 | 5/22/2026 |  |  |  |  | Prototype shipped at /app/lms/[slug]/page.tsx.
14 | Top-level dashboard UI | /dashboard landing for the learner across all enrollments. | Completed | Medium | 100 | 5/1/2026 | 5/22/2026 |  |  |  |  | Prototype shipped at /app/dashboard/page.tsx.
15 | Per-course dashboard variant UI | /dashboard/[course] alternate per-course surface. | Completed | Medium | 100 | 5/1/2026 | 5/22/2026 |  |  |  |  | Prototype shipped at /app/dashboard/[course]/page.tsx.
16 | Dashboard progress view UI | /dashboard/progress summary view across enrollments. | Completed | Medium | 100 | 5/1/2026 | 5/22/2026 |  |  |  |  | Prototype shipped at /app/dashboard/progress/page.tsx.
17 | Combo dashboard prototype UI | /dashboard-multi prototype for F+P-style combo learners with stacked sub-sections. | Completed | Medium | 100 | 5/1/2026 | 5/22/2026 |  |  |  |  | Prototype shipped at /app/dashboard-multi/page.tsx.
18 | Reference card viewer UI | /lms/[slug]/reference/[card] with left card list, body, prev/next, mark-as-read toggle, bookmark icon. Stage 3 screen 2. | Completed | Medium | 100 | 5/1/2026 | 5/22/2026 |  |  |  |  | Prototype shipped at /app/lms/[slug]/reference/[card]/page.tsx.
19 | Study guide viewer UI | /lms/[slug]/study-guide/[guide] with sticky TOC sidebar, anchor jumps, scroll progress. Stage 3 screen 3. | Completed | Medium | 100 | 5/1/2026 | 5/22/2026 |  |  |  |  | Prototype shipped at /app/lms/[slug]/study-guide/[guide]/page.tsx.
20 | Glossary UI | /lms/[slug]/glossary with searchable A-Z term list and expandable definitions. Stage 3 screen 4. | Completed | Medium | 100 | 5/1/2026 | 5/22/2026 |  |  |  |  | Prototype shipped at /app/lms/[slug]/glossary/page.tsx.
21 | Question bank topic picker UI | /lms/[slug]/question-bank topic-cluster picker with difficulty / wrong-only filters and session length selector. Stage 3 screen 5. | Completed | Medium | 100 | 5/1/2026 | 5/22/2026 |  |  |  |  | Prototype shipped at /app/lms/[slug]/question-bank/page.tsx.
22 | Question bank session runner UI | /lms/[slug]/question-bank/session/[id] one-question-at-a-time runner with explanation reveal. Stage 3 screen 6. | Completed | Medium | 100 | 5/1/2026 | 5/22/2026 |  |  |  |  | Prototype shipped at /app/lms/[slug]/question-bank/session/[id]/page.tsx.
23 | Question bank session results UI | /lms/[slug]/question-bank/session/[id]/result with per-topic breakdown and review CTAs. Stage 3 screen 7. | Completed | Medium | 100 | 5/1/2026 | 5/22/2026 |  |  |  |  | Prototype shipped at /app/lms/[slug]/question-bank/session/[id]/result/page.tsx.
24 | Mock exam intro UI | /lms/[slug]/mock-exam/[paperId] paper intro with format, question count, time, pass mark, warnings. Stage 3 screen 8. | Completed | Medium | 100 | 5/1/2026 | 5/22/2026 |  |  |  |  | Prototype shipped at /app/lms/[slug]/mock-exam/[paperId]/page.tsx.
25 | Mock exam runner UI (closed-book) | /lms/[slug]/mock-exam/[paperId]/run timed runner with sticky timer, question navigator, flag, auto-save. Stage 3 screen 9. | Completed | Medium | 100 | 5/1/2026 | 5/22/2026 |  |  |  |  | Prototype shipped at /app/lms/[slug]/mock-exam/[paperId]/run/page.tsx.
26 | Mock exam results UI | /lms/[slug]/mock-exam/[paperId]/result with pass/fail vs pass mark, per-topic chart, full question review. Stage 3 screen 11. | Completed | Medium | 100 | 5/1/2026 | 5/22/2026 |  |  |  |  | Prototype shipped at /app/lms/[slug]/mock-exam/[paperId]/result/page.tsx.
27 | Design tokens — tier theming (Bronze/Silver/Gold) | Color tokens, badge styles, and locked-tile chrome for the three tiers; consumed by every section and tile. | Completed | Critical | 100 | 6/1/2026 | 6/3/2026 |  |  |  |  | Tier theming tokens (--tier-bronze/silver/gold) + .tier-badge appended to /app/globals.css. Verified at /showcase.
28 | Status banner component | Sticky at-a-glance bar showing exam target, progress %, readiness 0-100, voucher state. Used across all dashboard variants. | Completed | High | 100 | 6/2/2026 | 6/4/2026 | Design tokens — tier theming (Bronze/Silver/Gold) | Banner uses tier color + badge tokens. | Pending | Mayank | StatusBanner.tsx component built; verified rendering Gold + Bronze variants at /showcase.
29 | Locked-tile component | Reusable locked tile with 🔒 chrome and 'Upgrade →' CTA. Drives Bronze-locked AI tiles and Silver-locked Gold-only tiles. | Completed | High | 100 | 6/2/2026 | 6/4/2026 | Design tokens — tier theming (Bronze/Silver/Gold) | Locked tile uses tier badge tokens. | Pending | Mayank | LockedTile.tsx component built with tier-aware Upgrade CTA; verified Silver + Gold variants at /showcase.
30 | Section nav, breadcrumbs & back-CTA component | Consistent header chrome ('← Back to Exam Preparation' style) for every inner screen. | Completed | Medium | 100 | 6/2/2026 | 6/4/2026 | Design tokens — tier theming (Bronze/Silver/Gold) | Inherits typography + spacing tokens. | Pending | Mayank | BackBar.tsx component built (back CTA + breadcrumb trail); verified at /showcase.
31 | Empty, loading & error state components | Skeleton loaders, empty-state illustrations, and error fallbacks for every list/card surface. | Completed | Medium | 100 | 6/3/2026 | 6/5/2026 | Design tokens — tier theming (Bronze/Silver/Gold) | Uses tokens for tone and color. | Pending | Mayank | EmptyState.tsx, SkeletonCard.tsx, ErrorFallback.tsx all built; verified at /showcase.
32 | Mock exam submit-confirmation modal | Overlay modal on the runner: 'X unanswered, Y flagged, Z remaining — submit anyway?'. Stage 3 screen 10. | Completed | High | 100 | 6/4/2026 | 6/6/2026 | Status banner component | Reuses modal primitives + tier-agnostic chrome. | Pending | Mayank | Prototype shipped inline at /app/lms/[slug]/mock-exam/[paperId]/run/page.tsx (#submit overlay block).
33 | Open-book mock exam runner variant | Scenario block + collapsible 'Open the manual' sidebar for Practitioner-level objective testing. Stage 3 Variation A. | Completed | High | 100 | 6/4/2026 | 6/8/2026 | Mock exam submit-confirmation modal | Builds on the closed-book runner UI patterns. | Pending | Mayank | Open-book mock runner shipped at /app/lms/[slug]/mock-exam/[paperId]/run-openbook/page.tsx. Scenario block + collapsible manual sidebar + 70-Q / 150-min / 55% pass-mark chrome. Verified at /lms/pmp/mock-exam/2/run-openbook.
34 | Tier-variant section view — Bronze locks | Reduced-tile section view with AI tiles locked and 'Upgrade →' CTAs. Stage 3 Variation C. | Completed | Medium | 100 | 6/5/2026 | 6/7/2026 | Locked-tile component | Renders locked Gold/Silver tiles. | Pending | Mayank | Bronze section view shipped at /app/lms/[slug]/bronze-view/page.tsx with 6 unlocked tiles + 6 locked AI/coaching tiles (Silver+Gold Upgrade CTAs). Verified at /lms/pmp/bronze-view.
35 | Combo dashboard polish — dual sub-sections | Polish /dashboard-multi into a full F+P stacked layout with two voucher tiles and two readiness targets. Stage 3 Variation B. | Completed | Medium | 100 | 6/5/2026 | 6/8/2026 | Status banner component | Renders two status banners (F + P). | Pending | Mayank | Combo F+P view shipped at /app/lms/[slug]/combo-view/page.tsx — two stacked sub-sections (knowledge vs application framing), dual voucher pills, two readiness banners, 'either exam' combo note. Verified at /lms/prince2-fp/combo-view.
36 | Bookmark sidebar + 'Saved' tile | Bookmark icon on reference cards and guides; 'Saved' tile on the dashboard for quick return. Stage 3 side flow. | Completed | Low | 100 | 6/6/2026 | 6/8/2026 | Section nav, breadcrumbs & back-CTA component | Bookmark icon lives in inner-screen chrome. | Pending | Mayank | Saved/bookmarks list shipped at /app/lms/[slug]/saved/page.tsx with type-tagged rows (card/guide/glossary) and remove control. Verified at /lms/pmp/saved.
37 | Cross-content search UI | Search bar in section header that surfaces matches across reference cards, study guides, and glossary. Stage 3 side flow. | Completed | Low | 100 | 6/6/2026 | 6/9/2026 | Glossary UI | Reuses the existing glossary search component. | Pending | Mayank | Cross-content search shipped at /app/lms/[slug]/search/page.tsx with content-type chip filters and inline <mark> term highlighting across cards/guides/glossary/qbank. Verified at /lms/pmp/search.
38 | AI tools section view tiles | Grid of AI tiles grouped under 'Exam Preparation — AI' and 'Active Learning — AI' with last-used and freshness stamps. Stage 4 screen 1. | Completed | High | 100 | 6/7/2026 | 6/9/2026 | Locked-tile component | Bronze sees the entire section as locked tiles. | Pending | Mayank | AI section view shipped at /app/lms/[slug]/ai/page.tsx with two groups (Exam Prep AI, Active Learning AI) and freshness flags. Verified at /lms/pmp/ai.
39 | AI study plan UI | /lms/[slug]/ai/study-plan vertical calendar to exam date, daily activities, last-generated header. Silver vs Gold variants. Stage 4 screen 2. | Completed | High | 100 | 6/8/2026 | 6/12/2026 | AI tools section view tiles | Reached from the AI section tile. | Pending | Mayank | AI study plan shipped at /app/lms/[slug]/ai/study-plan/page.tsx with vertical calendar, today/rest/exam-day flags, per-activity deep links. Verified at /lms/pmp/ai/study-plan.
40 | AI gap report UI | /lms/[slug]/ai/gap-report topic-cluster strength chart, 3-5 prioritised actions, plain-language narrative. Stage 4 screen 3. | Completed | High | 100 | 6/9/2026 | 6/12/2026 | AI tools section view tiles | Reached from the AI section tile. | Pending | Mayank | AI gap report shipped at /app/lms/[slug]/ai/gap-report/page.tsx with topic strength bar chart, narrative summary, 5 numbered actions. Verified at /lms/pmp/ai/gap-report.
41 | Adaptive flashcards UI | /lms/[slug]/ai/flashcards card front/back flip, Again/Hard/Good/Easy self-rate, due-count stats. Drill Mode variant for Gold. Stage 4 screen 4. | Completed | Medium | 100 | 6/9/2026 | 6/13/2026 | AI tools section view tiles | Reached from the AI section tile. | Pending | Mayank | Adaptive flashcards shipped at /app/lms/[slug]/ai/flashcards/page.tsx with front/back face, SM-2 rate buttons (Again/Hard/Good/Easy), today-deck side list. Verified at /lms/pmp/ai/flashcards.
42 | AI concept coach chat UI | /lms/[slug]/ai/concept-coach chat window with citation links into Stage 3 content. Stage 4 screen 5. | Completed | High | 100 | 6/10/2026 | 6/14/2026 | AI tools section view tiles | Reached from the AI section tile. | Pending | Mayank | Concept coach chat shipped at /app/lms/[slug]/ai/concept-coach/page.tsx with citation chips and suggested follow-ups. Verified at /lms/pmp/ai/concept-coach.
43 | AI scenario coach branching dialogue UI | /lms/[slug]/ai/scenario-coach scenario picker → 4-6 turn branching dialogue → rubric summary. Practitioner-only, not rendered on Foundation. Stage 4 screen 6. | Completed | Medium | 100 | 6/11/2026 | 6/15/2026 | AI concept coach chat UI | Reuses the chat surface shell. | Pending | Mayank | Scenario coach shipped at /app/lms/[slug]/ai/scenario-coach/page.tsx with scenario picker, branching options, rubric panel. Verified at /lms/pmp/ai/scenario-coach.
44 | AI interview coach chat UI | /lms/[slug]/ai/interview-coach role picker, 5-10 mock questions, per-answer feedback. Lives under Support section. Stage 4 screen 7. | Completed | Low | 100 | 6/12/2026 | 6/15/2026 | AI concept coach chat UI | Reuses the chat surface shell. | Pending | Mayank | Interview coach shipped at /app/lms/[slug]/ai/interview-coach/page.tsx with STAR rubric pills and feedback turns. Verified at /lms/pmp/ai/interview-coach.
45 | Daily AI challenge UI | /lms/[slug]/ai/daily-challenge daily scenario, reveal-model-answer, optional cohort comments. Stage 4 screen 8. | Completed | Low | 100 | 6/12/2026 | 6/15/2026 | AI tools section view tiles | Reached from the AI section tile. | Pending | Mayank | Daily AI challenge shipped at /app/lms/[slug]/ai/daily-challenge/page.tsx with hero scenario, archive list, cohort comments. Verified at /lms/pmp/ai/daily-challenge.
46 | AI chat refusal / out-of-scope state | Out-of-syllabus refusal copy with 3 in-scope suggestions. No 'I don't know' — always redirects. Stage 4 side flow. | Completed | Medium | 100 | 6/13/2026 | 6/15/2026 | AI concept coach chat UI | Adds a refusal sub-state to the chat surface. | Pending | Mayank | Out-of-syllabus refusal state shipped at /app/lms/[slug]/ai/states/refusal/page.tsx — redirect with 3 in-scope suggestions, no 'I don't know'. Verified at /lms/pmp/ai/states/refusal.
47 | Plan re-generation diff modal | Diff modal showing which days changed and why, before overwriting the AI study plan. Stage 4 side flow. | Completed | Low | 100 | 6/13/2026 | 6/15/2026 | AI study plan UI | Triggered from 'Re-generate plan' CTA. | Pending | Mayank | Plan re-generation diff modal shipped at /app/lms/[slug]/ai/states/plan-diff/page.tsx with ADD/REMOVE/SHIFT tags. Verified at /lms/pmp/ai/states/plan-diff.
48 | AI cost-cap reached state | 'Daily limit reached — resumes in HH:MM' empty state for the chat surface. Stage 4 side flow. | Completed | Low | 100 | 6/13/2026 | 6/15/2026 | AI concept coach chat UI | Empty-state variant of the chat surface. | Pending | Mayank | Cost-cap reached state shipped at /app/lms/[slug]/ai/states/cap-reached/page.tsx — no upsell, redirects to flashcards/study plan. Verified at /lms/pmp/ai/states/cap-reached.
49 | Support & mentoring section view | Section header + tile group on the dashboard for Live training · Q&A · Coaching · Support · Community · Cashback · Money-back · Attendance cert. Stage 5 screen 1. | Completed | High | 100 | 6/8/2026 | 6/10/2026 | LMS course dashboard shell UI | Extends the existing dashboard with the Support group. | Pending | Mayank | Prototype shipped at /app/lms/[slug]/page.tsx — Support & Mentoring section (8 tiles) appended between Simulation Papers and Readiness Score. Verified at /lms/pmp.
50 | Live training schedule UI | /lms/[slug]/live-training calendar of session blocks with timezone, instructor, capacity, RSVP. Stage 5 screen 2. | Completed | High | 100 | 6/9/2026 | 6/13/2026 | Support & mentoring section view | Reached from the Support section. | Pending | Mayank | Prototype shipped at /app/lms/[slug]/live-training/page.tsx. Calendar of session blocks with timezone selector, RSVP states (Open/Joined/Full/Waitlist/LIVE), instructor avatars, capacity bars. Verified at /lms/pmp/live-training.
51 | Live session detail UI | /lms/[slug]/live-training/[sessionId] topic, objectives, instructor bio, pre-reading deep-link, 'Join session' CTA. Stage 5 screen 3. | Completed | Medium | 100 | 6/10/2026 | 6/13/2026 | Live training schedule UI | Drill-down from a schedule block. | Pending | Mayank | Prototype shipped at /app/lms/[slug]/live-training/[sessionId]/page.tsx. Hero with Join CTA, objectives, agenda timeline, instructor bio, pre-reading deep-links, peer attendees, related sessions, system-check footer. Verified at /lms/pmp/live-training/s-25-1.
52 | Q&A session booking UI | /lms/[slug]/qa-session recurring slots list with instructor on duty and RSVP state. Stage 5 screen 4. | Completed | Medium | 100 | 6/11/2026 | 6/14/2026 | Support & mentoring section view | Reached from the Support section. | Pending | Mayank | Prototype shipped at /app/lms/[slug]/qa-session/page.tsx. Recurring weekly schedule (5 templates), 7 upcoming slots with instructor-on-duty + all RSVP states (incl. glowing LIVE Join now), past Q&A recordings library. Verified at /lms/pmp/qa-session.
53 | 1:1 coaching booking UI | /lms/[slug]/coaching credits remaining, available slots, pre-call prep questionnaire. Gold-only. Stage 5 screen 5. | Completed | Medium | 100 | 6/11/2026 | 6/14/2026 | Locked-tile component | Silver/Bronze see locked-tile entry. | Pending | Mayank | Prototype shipped at /app/lms/[slug]/coaching/page.tsx (Gold-only). Credits hero (3/6), 4 coach cards, 7-day slot grid with 4 slot states (Open/Selected/Yours/Blocked), pre-call prep questionnaire with answered+pending states, sticky booking summary, past sessions. Verified at /lms/pmp/coaching.
54 | Support inbox UI | /lms/[slug]/support open/resolved ticket list, composer, tier-aware channel badges (email/chat/phone). Stage 5 screen 6. | Completed | High | 100 | 6/12/2026 | 6/15/2026 | Support & mentoring section view | Reached from the Support section. | Pending | Mayank | Prototype shipped at /app/lms/[slug]/support/page.tsx. Tier-aware channel badges (Email/Chat/Phone), ticket list with category/status/channel pills, all 4 ticket states (Open/Waiting-on-you/In-progress/Resolved), composer with channel picker (locked variant for sub-Gold tiers), SLA card, help articles. Verified at /lms/pmp/support.
55 | Ticket thread UI | /lms/[slug]/support/[ticketId] thread view with attachments, status, and 'Call us now' button when Gold + online. Stage 5 screen 7. | Completed | Medium | 100 | 6/13/2026 | 6/16/2026 | Support inbox UI | Drill-down from inbox. | Pending | Mayank | Prototype shipped at /app/lms/[slug]/support/[ticketId]/page.tsx. Message thread with learner/agent/system events, inline attachments with type-specific icons, channel tag per message, reply composer with Reply/Internal note tabs, prominent green Call-us-now button (Gold+online), phone-support card with pulsing online dot, related tickets. Verified at /lms/pmp/support/TCK-4821.
56 | Community access UI | /lms/[slug]/community landing with code of conduct and 'Join the community' CTA. Stage 5 screen 8. | Completed | Low | 100 | 6/13/2026 | 6/15/2026 | Support & mentoring section view | Reached from the Support section. | Pending | Mayank | Prototype shipped at /app/lms/[slug]/community/page.tsx. 4-stat hero, perks grid, 6 channels with unread badges, 6-rule code of conduct with Do/Dont examples, featured discussions preview (with Pinned tag), top contributors with Mod pills, sticky dark Join CTA with code-of-conduct checkbox, privacy panel, TL;DR. Verified at /lms/pmp/community.
57 | Cashback ledger UI | /lms/[slug]/cashback ledger lines, accrual events, payout history, payout request CTA. Stage 5 screen 9. | Completed | Medium | 100 | 6/14/2026 | 6/16/2026 | Support & mentoring section view | Reached from the Support section. | Pending | Mayank | Prototype shipped at /app/lms/[slug]/cashback/page.tsx. Green gradient balance hero (Rs.1,850 available), 4 stat cards (lifetime/paid-out/pending/milestones), ledger with 9 entries covering all states (credited, pending amber, rejected with reason callout, payout completed with TXN ID), referral code IL-VK-9X4, payout request panel, 6-source earning guide, referral share buttons. Verified at /lms/pmp/cashback.
58 | Money-back guarantee panel UI | /lms/[slug]/money-back terms, gate-progress checklist mirror, claim form CTA greyed out until fail recorded. Gold-only. Stage 5 screen 10. | Completed | High | 100 | 6/15/2026 | 6/18/2026 | Status banner component | Mirrors gate-progress state from the banner. | Pending | Mayank | Prototype shipped at /app/lms/[slug]/money-back/page.tsx (Gold-only). Dark coverage hero (Rs.24,500), claim state card with disabled Claim form locked until exam result is recorded CTA (dashed border), 6-item gate-progress checklist mirror with 4 state tints (Met/In-progress/At-risk/Blocked) and per-item action buttons, 8 plain-language terms, 4-step claim flow, refund-to card. Verified at /lms/pmp/money-back.
59 | Attendance certificate UI | /lms/[slug]/certificates/attendance auto-generated PDF preview with download and LinkedIn share. Stage 5 screen 11. | Completed | Low | 100 | 6/15/2026 | 6/17/2026 | Support & mentoring section view | Reached from the Support section. | Pending | Mayank | Prototype shipped at /app/lms/[slug]/certificates/attendance/page.tsx. Auto-generated certificate preview with gold double border, ornate corners, Georgia serif typography, learner name with gold underline, cursive signature blocks for trainer + signatory, gold dashed Verified seal, certificate number INV-PMP-2026-04821. Sidebar: Download PDF + LinkedIn share + 4-icon share row + recent attendance log. Verified at /lms/pmp/certificates/attendance.
60 | Reschedule / cancel modals | Modal copy for live session reschedule (24h cutoff), coaching cancel (12h forfeit), and support tier-mismatch lock state. Stage 5 side flows. | Completed | Low | 100 | 6/16/2026 | 6/18/2026 | Live training schedule UI | Triggered from session and coaching surfaces. | Pending | Mayank | Prototype shipped at /app/lms/[slug]/states/modals/page.tsx. Showcase of 3 modals as overlays on dimmed striped stages: (1) Live session reschedule (blue, with 3 radio slot options + Best match pill) (2) Coaching cancel with red top border (credits-burn impact grid 3->2 + alternate suggestion + confirm checkbox) (3) Tier-mismatch lock with gold top border (Silver->Gold comparison + perks list + Rs.8,000 upgrade cost panel). Verified at /lms/pmp/states/modals.
61 | Readiness panel overview UI | /lms/[slug]/readiness composite 0-100 score, three input cards (Mocks · Q-bank · Gap-report), projected ready-by date, refresh CTA. Stage 6 screen 1. | Completed | Critical | 100 | 6/15/2026 | 6/19/2026 | Status banner component | Banner deep-links into this panel. | Pending | Mayank | Prototype shipped at /app/lms/[slug]/readiness/page.tsx. Composite-score conic ring (62/100), green projection card (8 Jun 2026, moderate confidence), 3 weighted input cards (Mocks/Q-bank/Gap-acks colour-keyed with weight badges + delta pills), custom SVG trend chart with actual+projected lines and pass-threshold marker, ranked actions list, 3-tier weighting comparison (Bronze/Silver/Gold). Verified at /lms/pmp/readiness.
62 | Readiness — mocks drill-down UI | /lms/[slug]/readiness/mocks per-paper scores, threshold checks, remaining-attempts hint, jump-to-next-mock CTA. Stage 6 screen 2. | Completed | High | 100 | 6/16/2026 | 6/19/2026 | Readiness panel overview UI | Drill-down card on the panel. | Pending | Mayank | Prototype shipped at /app/lms/[slug]/readiness/mocks/page.tsx. 4-stat strip (Attempted/Above pass/Above target/Best&avg), dark contribution card, threshold-check hint with colour-coded dots, per-paper list of 6 mocks with attempt history rows + outcome pills (above-target/pass/below-target/below-pass), mini progress tracks with pass+target tick marks, recommended-next + locked-paper states, topic-cluster breakdown with band classification, green-gradient footer CTA. Verified at /lms/pmp/readiness/mocks.
63 | Readiness — Q-bank coverage drill-down UI | /lms/[slug]/readiness/qbank topic-cluster heatmap with <50% floor highlighting and deep-link into the picker. Stage 6 screen 3. | Completed | High | 100 | 6/16/2026 | 6/19/2026 | Readiness panel overview UI | Drill-down card on the panel. | Pending | Mayank | Prototype shipped at /app/lms/[slug]/readiness/qbank/page.tsx. Below-floor stat + heatmap grid (cluster x difficulty) with cells colour-coded by accuracy and red-bordered when below 50% coverage floor. Per-row coverage track with floor marker, accuracy band pill, wrong-pool count, Drill/Cover-gap CTA. Plus wrong-answers bar chart per cluster, 3 ranked drill suggestions with deep-links into Q-bank picker. Verified at /lms/pmp/readiness/qbank.
64 | Readiness — gap-report ack drill-down UI | /lms/[slug]/readiness/gap-reports list of past gap reports with ack state and unacked links into Stage 4. Stage 6 screen 4. | Completed | Medium | 100 | 6/17/2026 | 6/20/2026 | Readiness panel overview UI | Drill-down card on the panel. | Pending | Mayank | Prototype shipped at /app/lms/[slug]/readiness/gap-reports/page.tsx. Timeline of 4 past gap reports (latest-first) with marker dots colour-coded by ack state (unacked amber + GATING red flag, acked blue, acted green, stale grey). Each card shows summary, top contributing clusters with bars, recommended actions checklist (deep-linked into Stage 4 surfaces), ack date footer, Acknowledge primary CTA when unacked. Verified at /lms/pmp/readiness/gap-reports.
65 | Voucher tile — locked + unlocked states | Dashboard voucher tile with the locked state (lock badge, 'N points to unlock', panel link) and the unlocked state (glowing border, 'Ready to redeem' CTA). Stage 6 screens 5-6. | Completed | Critical | 100 | 6/17/2026 | 6/20/2026 | Status banner component | Banner mirrors the tile state. | Pending | Mayank | Prototype shipped at /app/lms/[slug]/voucher/page.tsx. Showcase of all 4 voucher tile states: Locked (gray, 13 points to unlock), Almost (amber, 2 points fire icon), Unlocked (glowing green with pulse animation, big Redeem CTA), Redeemed (dark navy, voucher code in dashed box). Gates list under each tile colour-coded by status. Verified at /lms/pmp/voucher.
66 | Voucher reveal modal UI | Modal overlay with awarding-body logo, cert level, voucher code, validity window, copy button, 'Open booking page' CTA. Stage 6 screen 7. | Completed | Critical | 100 | 6/18/2026 | 6/21/2026 | Voucher tile — locked + unlocked states | Triggered from 'Redeem voucher'. | Pending | Mayank | Prototype shipped at /app/lms/[slug]/voucher/modals/page.tsx (reveal modal). Awarding-body logo (PMI), PMP exam voucher title, code in big dashed yellow box with green Copy button, 3 green checkmarks (single-use/locked-to-you/guarantee-active), yellow warning, confetti sparkles, I-will-book-later + Open-booking-page CTAs. Verified at /lms/pmp/voucher/modals.
67 | Awarding-body booking handoff UI | /lms/[slug]/voucher/booking explainer page handing off to PeopleCert/PMI/APMG with steps and the external booking URL. Stage 6 screen 8. | Completed | High | 100 | 6/19/2026 | 6/22/2026 | Voucher reveal modal UI | Reached after voucher reveal. | Pending | Mayank | Prototype shipped at /app/lms/[slug]/voucher/booking/page.tsx. PMI handoff page: hero with PMI logo + booking blurb + 3 meta tiles (validity/format/lead time) + blue Open PMI booking page primary CTA, sticky voucher card (yellow-tinted, dashed code box, dl details), 4-step booking guide with tips, FAQ list, support card with 3 channels (email/phone-Gold/PMI direct), dark Already-booked? footer linking to record exam date. Verified at /lms/pmp/voucher/booking.
68 | Exam scheduled state UI | /lms/[slug]/voucher/scheduled date-capture form; banner transitions to 'Exam: <date> · N days away'. Stage 6 screen 9. | Completed | High | 100 | 6/20/2026 | 6/23/2026 | Awarding-body booking handoff UI | Captured after the learner books externally. | Pending | Mayank | Prototype shipped at /app/lms/[slug]/voucher/scheduled/page.tsx. Confirmed state: blue gradient hero (Friday 12 June 2026), big yellow countdown ring (17 days), exam day checklist (5 items, 3 done), suggested countdown taper (T-14 -> Exam day timeline), banner-mirror note. Form variant also defined for the date-capture state. Verified at /lms/pmp/voucher/scheduled.
69 | Combo voucher view — two tiles, two gates | Side-by-side Foundation + Practitioner voucher tiles with independent gate states. Stage 6 screen 10. | Completed | Medium | 100 | 6/21/2026 | 6/23/2026 | Voucher tile — locked + unlocked states | Variant of the single voucher tile. | Pending | Mayank | Prototype shipped at /app/lms/[slug]/voucher/combo/page.tsx. Side-by-side Foundation + Practitioner tiles with independent gate states (Foundation redeemed/booked dark navy, Practitioner locked grey with 17 points to unlock). Each tile shows gate list, validity window, and tier-appropriate CTA. Combo-path guide + money-back-across-combo explainer. Verified at /lms/pmp/voucher/combo.
70 | Early-redeem override confirmation modal | Hard-confirm modal that explicitly forfeits the Gold money-back guarantee. Stage 6 side flow. | Completed | Medium | 100 | 6/21/2026 | 6/23/2026 | Voucher tile — locked + unlocked states | Triggered from a support-routed override. | Pending | Mayank | Prototype shipped at /app/lms/[slug]/voucher/modals/page.tsx (override modal). Red top border, triangle warning icon, Redeem-voucher-before-gate-cleared headline, state strip (62 composite -> Rs.24,500 forfeit), red What-youre-giving-up list (guarantee/refund/retake), green What-stays-the-same list, grey audit log note, 2 required confirmation checkboxes, disabled red Redeem-early-and-forfeit-guarantee CTA. Verified at /lms/pmp/voucher/modals.
71 | Exam day prep UI | /lms/[slug]/exam-day countdown, day-of checklist (ID, system req, quiet room), policies summary. Stage 7 screen 1. | Completed | High | 100 | 6/19/2026 | 6/22/2026 | Exam scheduled state UI | Reached as the scheduled date approaches. | Pending | Mayank | Prototype shipped at /app/lms/[slug]/exam-day/page.tsx. Dark countdown chip in head, 4-card exam meta strip (cert/when/format/booking), blue gradient countdown card with days+hours+checklist progress, day-of checklist grouped by 4 categories (Identity/Tech/Environment/Policies) with check states, 5 PMI policies (numbered list), red watch-outs card, dark CTA banner linking to standby surface. Verified at /lms/pmp/exam-day.
72 | Exam day standby UI | /lms/[slug]/exam-day/active calm 'Good luck' surface with study tools disabled during the exam window. Stage 7 screen 2. | Completed | Medium | 100 | 6/20/2026 | 6/22/2026 | Exam day prep UI | Auto-routed during the booked window. | Pending | Mayank | Prototype shipped at /app/lms/[slug]/exam-day/active/page.tsx. Calm centered surface with LIVE/SOON pulsing status pill, big Join exam now green CTA (or yellow countdown numbers when soon), final reminders list (4 checks + 1 info), amber locked panel announcing that study tools are paused during the exam window, footer with support + outcome-recording links. Verified at /lms/pmp/exam-day/active.
73 | Outcome recording UI | /lms/[slug]/exam-result/record form for pass/fail, score, date, optional proof upload. Stage 7 screen 3. | Completed | Critical | 100 | 6/20/2026 | 6/23/2026 | Exam day standby UI | Reached post-exam. | Pending | Mayank | Prototype shipped at /app/lms/[slug]/exam-result/record/page.tsx. Outcome picker tiles (Pass green / Fail red) with radio selection, 5-field form (date / score / booking ref / delivery method / notes), dashed upload zone for proof, sidebar showing What happens next per tier (Bronze repurchase, Silver 1x90d retake, Gold 2x180d + claim) + why-proof block + yellow one-time-entry warning. Verified at /lms/pmp/exam-result/record.
74 | Pass — certificate page UI | /lms/[slug]/certificate awarding-body cert mirror, learner name, date earned, validity, download PDF button. Stage 7 screen 4. | Completed | High | 100 | 6/22/2026 | 6/25/2026 | Outcome recording UI | Surfaced on pass. | Pending | Mayank | Prototype shipped at /app/lms/[slug]/certificate/page.tsx. Blue-themed certificate frame (double border + ornate corners + dashed PMI seal in centre + cursive signatures of Pierre Le Manh and Sunil Prashara) showing PMP certification number, score AT/AT/T, valid-through date. Sidebar: Download PDF + Share-on-LinkedIn + 4-icon share row, certificate details dl, three-link Whats next card (share / pathways / renewal). Verified at /lms/pmp/certificate.
75 | Pass — social share UI | /lms/[slug]/share LinkedIn/X/WhatsApp preview cards with referral attribution to invensislearning.com. Stage 7 screen 5. | Completed | Medium | 100 | 6/23/2026 | 6/25/2026 | Pass — certificate page UI | Reached from the certificate page. | Pending | Mayank | Prototype shipped at /app/lms/[slug]/share/page.tsx. Three pre-built share cards (LinkedIn blue / X dark / WhatsApp green) with platform-accurate mockups: LinkedIn post with avatar+cert-attachment, X 280-char short, WhatsApp chat bubble in green theme. Edit + Post CTAs per card. Yellow referral payoff card with +Rs.600 bonus and copy-code button + cashback link. Dark Whats next footer. Verified at /lms/pmp/share.
76 | Pass — post-cert pathways UI | /lms/[slug]/pathways curated next-step recommendations linking back to invensislearning.com. Stage 7 screen 6. | Completed | Medium | 100 | 6/23/2026 | 6/26/2026 | Pass — certificate page UI | Reached from the certificate page. | Pending | Mayank | Prototype shipped at /app/lms/[slug]/pathways/page.tsx. Six curated certifications (PgMP/PMI-ACP/PMI-RMP/PRINCE2 Practitioner/ITIL 4 DPI/Lean Six Sigma BB) in 3-col grid colour-keyed by track. Each card: difficulty pill (Advanced/Lateral/Specialise) + awarding body chip + Why-match green callout grounded in learner signals + colored CTA opening invensislearning.com. Top match highlighted on PgMP. Dark alumni-discount footer. Verified at /lms/pmp/pathways.
77 | Pass — renewal cycle tracker UI | /lms/[slug]/renewal validity window, PDU tracker for PMP, re-registration countdown for PRINCE2 Practitioner / ITIL 4. Stage 7 screen 7. | Completed | Medium | 100 | 6/24/2026 | 6/27/2026 | Pass — certificate page UI | Reached from the certificate page. | Pending | Mayank | Prototype shipped at /app/lms/[slug]/renewal/page.tsx. Blue PDU progress hero (12/60) with cycle marker showing on-track vs behind, two category bars (Education 8/35 + Giving back 4/25), 4-entry PDU activity log auto-synced from PMI CCR, opportunity sidebar with 4 ways to earn (training/mentor/case study/webinars), dark What-happens-if-you-dont-renew footer linking to PMI CCR Handbook. Verified at /lms/pmp/renewal.
78 | Fail — outcome view UI | /lms/[slug]/exam-result tier-aware recovery paths: Bronze re-purchase, Silver retake (1×90d), Gold retake (2×180d) + claim. Stage 7 screen 8. | Completed | High | 100 | 6/23/2026 | 6/26/2026 | Outcome recording UI | Surfaced on fail. | Pending | Mayank | Prototype shipped at /app/lms/[slug]/exam-result/page.tsx. Empathetic Tough day. Heres the path forward header with Did not pass red pill, red-tinted score hero (54% with red marker at 60 pass mark + closest-cluster meta), tier card explaining tier-aware recovery, side-by-side path picker: Retake 180 days (green Recommended) + Money-back claim (amber Gate-honoured). Per-cluster weakness chart + Setback-not-verdict tone card. Verified at /lms/pmp/exam-result.
79 | Fail — retake training booking UI | /lms/[slug]/retake retake schedule tagged from live training, credit ledger, re-attempt window banner. Stage 7 screen 9. | Completed | Medium | 100 | 6/24/2026 | 6/27/2026 | Fail — outcome view UI | Reached from the fail view. | Pending | Mayank | Prototype shipped at /app/lms/[slug]/retake/page.tsx. Window status hero (168 of 180 days left + voucher Re-issued pill), 3-cohort picker with capacity bars + recommended highlight, credit ledger card showing 4 included resources (training/Q-bank boost/extra mocks/coaching), 6-week suggested taper plan timeline, amber Not feeling the retake? banner offering claim alternative. Verified at /lms/pmp/retake.
80 | Fail — money-back claim form UI | /lms/[slug]/money-back/claim pre-populated form, gate-honoured checklist mirror, bank/UPI block. Stage 7 screen 10. | Completed | Critical | 100 | 6/24/2026 | 6/27/2026 | Fail — outcome view UI | Reached from the fail view (Gold). | Pending | Mayank | Prototype shipped at /app/lms/[slug]/money-back/claim/page.tsx. Refund-amount green hero (Rs.23,000 = Rs.24,500 - Rs.1,500 cashback) with claim window meta, 6-item gate-honoured checklist mirror with snapshot-at-redemption columns (all OK in demo), 3 payout method radios, claim form with required proof upload, two required confirmation checkboxes, danger red Submit refund claim CTA (disabled until checkboxes ticked). How-claim-flows + Talk-to-coach sidebar. Verified at /lms/pmp/money-back/claim.
81 | Fail — refund status timeline UI | /lms/[slug]/money-back/status/[claimId] submitted/verified/approved/rejected/refunded timeline with rejection reason. Stage 7 screen 11. | Completed | High | 100 | 6/25/2026 | 6/28/2026 | Fail — money-back claim form UI | Drill-down after claim submit. | Pending | Mayank | Prototype shipped at /app/lms/[slug]/money-back/status/[claimId]/page.tsx. Dark refund hero (Rs.23,000 + claim meta + expected-by date), Currently-doing card spelling the active step, 4-step timeline with state-colored dots (done green / current blue pulsing / pending dashed / rejected red) and connecting line, dispute callout that only renders when rejected, audit receipt dl + What happens after refund sidebar. Verified at /lms/pmp/money-back/status/CLM-2026-7841.
82 | Closed enrollment terminal-state UI | /lms/[slug] terminal state: closed (passed) or closed (refunded), compact summary, cross-sell back to invensislearning.com. Stage 7 screen 12. | Completed | Medium | 100 | 6/26/2026 | 6/29/2026 | Pass — certificate page UI | Reached from pass or refund terminal. | Pending | Mayank | Prototype shipped at /app/lms/[slug]/closed/page.tsx. Two terminal variants: PASSED — golden gradient hero with PMP-certified strong + trophy circle + Download/Share/Renewal CTAs; REFUNDED — dark hero with refund-amount card + re-enrol-at-alumni-rate. Both show 6-stat journey summary, 3-card pathways cross-sell (PgMP/PMI-ACP/LSSBB), green What-you-keep + grey Whats-archived split, warm Glad-you-came-through-with-us footer with alumni community CTA. Verified at /lms/pmp/closed.
83 | Email template designs (welcome, activation, receipt, nudges) | Static HTML mockups for the transactional emails referenced in Stages 1, 2 and 5 — visual only, not wired to a sender. | Pending | Medium | 0 | 6/8/2026 | 6/12/2026 | Design tokens — tier theming (Bronze/Silver/Gold) | Inherits brand tokens for visual consistency. | Pending | Mayank
84 | Instructor profile modal | Bio modal with qualifications + learner ratings, triggered from any instructor name across Stage 5. Side flow. | Pending | Low | 0 | 6/13/2026 | 6/15/2026 | Live session detail UI | Triggered from instructor name on schedule/Q&A. | Pending | Mayank
85 | Almost-there celebration banner | Composite-score ≥90 celebratory banner on the dashboard ('One more mock and you're ready'). Stage 6 side flow. | Pending | Low | 0 | 6/19/2026 | 6/21/2026 | Status banner component | Variant state of the at-a-glance banner. | Pending | Mayank
86 | Accessibility + responsive pass on all screens | WCAG 2.2 AA keyboard nav, screen-reader labels, focus management, contrast, mobile + tablet breakpoints across every UI prototype. | Pending | High | 0 | 6/26/2026 | 6/30/2026 | Closed enrollment terminal-state UI | Final pass once all screens exist. | Pending | Mayank
87 | Auth session + RBAC middleware wiring | JWT/cookie session, role-based gates, and route protection across /lms, /dashboard, /onboarding. Underpins every authenticated screen. | Pending | Critical | 0 | 7/1/2026 | 7/4/2026 | Set-password & T&C UI | Set-password handshake mints the session this layer manages. | Completed | Mayank
88 | Learner + enrollment data model | User, enrollment, tier, course-slug, status fields with persistence and migrations. Source of truth for every dashboard read. | Pending | Critical | 0 | 7/1/2026 | 7/5/2026 | LMS course dashboard shell UI | Dashboard reads enrollment + tier from this model. | Completed | Mayank
89 | Course catalog data model | Courses, Bronze/Silver/Gold packages, exam specs (pass mark, time limit, format), and per-tier feature flags. Drives tile rendering. | Pending | Critical | 0 | 7/1/2026 | 7/6/2026 | LMS course dashboard shell UI | Catalog drives which tiles render on the dashboard. | Completed | Mayank
90 | Content authoring schema | Schema + storage for reference cards, study guides, glossary, question bank, and mock papers, tagged by course x tier. | Pending | High | 0 | 7/2/2026 | 7/8/2026 | Course catalog data model | All Stage 3 content lives under this schema. | Pending | Mayank
91 | Tier-gating middleware | Server-side filter that hides or renders-locked any feature above the enrollment's tier; emits 'Upgrade ->' affordances. | Pending | High | 0 | 7/5/2026 | 7/8/2026 | Learner + enrollment data model | Reads enrollment.tier and filters payloads. | Pending | Mayank
92 | Activation token endpoint wiring | GET /activate/[token] resolves to enrollment + course summary; expired-token fallback that triggers a fresh activation email. | Pending | High | 0 | 7/6/2026 | 7/8/2026 | Activation landing page UI | Token resolves to enrollment record. | Completed | Mayank
93 | Set-password endpoint + auto-login wiring | POST /auth/activate to set password, mint session, and redirect into onboarding. | Pending | High | 0 | 7/6/2026 | 7/8/2026 | Set-password & T&C UI | Form submission hits this endpoint. | Completed | Mayank
94 | Login endpoint + multi-enrollment routing wiring | POST /auth/login authenticates and routes: single enrollment -> /lms/[slug]; multi -> /dashboard. | Pending | High | 0 | 7/7/2026 | 7/9/2026 | Return login UI | Login form posts to this endpoint. | Completed | Mayank
95 | Forgot-password request + reset-email wiring | POST /auth/forgot-password issues short-lived reset token and queues the reset email. | Pending | Medium | 0 | 7/8/2026 | 7/10/2026 | Forgot-password request UI | Request form posts to this endpoint. | Completed | Mayank
96 | Reset-password endpoint wiring | Validate token + POST new password; invalidates old sessions and redirects to login. | Pending | Medium | 0 | 7/8/2026 | 7/10/2026 | Reset password UI | Reset form posts to this endpoint. | Completed | Mayank
97 | Welcome + multi-enrollment routing wiring | Detect single vs multi enrollment after login; route to the right welcome surface and persist 'started onboarding' state. | Pending | Medium | 0 | 7/9/2026 | 7/10/2026 | Onboarding welcome UI | Decides which welcome surface to show. | Completed | Mayank
98 | Profile capture API wiring | POST onboarding step 1 (role, years, domain, study hours, English proficiency) and persist to enrollment profile. | Pending | High | 0 | 7/9/2026 | 7/11/2026 | Profile capture UI | Form posts to this endpoint. | Completed | Mayank
99 | Exam date API + countdown/cadence compute | POST exam target date; compute weeks-to-exam and recommended study cadence from profile.studyHours. | Pending | High | 0 | 7/10/2026 | 7/12/2026 | Exam target date UI | Form posts to this endpoint. | Completed | Mayank
100 | Baseline mock runtime + scoring wiring | Serve 20 baseline questions, time the attempt, score per topic cluster, persist as enrollment.baselineScore, feed AI gap inputs. | Pending | High | 0 | 7/10/2026 | 7/14/2026 | Baseline mock UI | Runner reads/writes through this endpoint. | Completed | Mayank
101 | Onboarding-complete transition wiring | Flip enrollment.status from 'activated' to 'active', stamp onboardedAt, and unlock the LMS dashboard. | Pending | Medium | 0 | 7/13/2026 | 7/14/2026 | Onboarding complete UI | CTA hits this transition endpoint. | Completed | Mayank
102 | Course dashboard data load wiring | Hydrate /lms/[slug] with enrollment, tier, section data, readiness score, voucher status, and recommended next steps. | Pending | High | 0 | 7/14/2026 | 7/17/2026 | LMS course dashboard shell UI | Shell consumes this payload. | Completed | Mayank
103 | Top-level + progress dashboard data load wiring | Load /dashboard and /dashboard/progress payloads (enrollments list, aggregate progress, readiness summaries). | Pending | Medium | 0 | 7/14/2026 | 7/17/2026 | Top-level dashboard UI | Both surfaces share this loader. | Completed | Mayank
104 | Combo dashboard data load wiring | Hydrate /dashboard-multi with the two sub-section payloads (F + P), two voucher states, two readiness scores. | Pending | Medium | 0 | 7/15/2026 | 7/18/2026 | Combo dashboard prototype UI | Multi-section surface consumes this payload. | Completed | Mayank
105 | Reference card load + mark-as-read state wiring | Fetch card body by slug, persist mark-as-read per learner, emit progress delta on the dashboard. | Pending | Medium | 0 | 7/15/2026 | 7/17/2026 | Reference card viewer UI | Viewer reads/writes through this endpoint. | Completed | Mayank
106 | Study guide load + scroll-progress wiring | Fetch guide body with ToC anchors; debounce scroll progress writes; resume position on return. | Pending | Medium | 0 | 7/16/2026 | 7/18/2026 | Study guide viewer UI | Viewer reads/writes through this endpoint. | Completed | Mayank
107 | Glossary load + cross-reference wiring | Serve A-Z terms with search index; expand-on-click and cross-reference links into cards/guides. | Pending | Low | 0 | 7/16/2026 | 7/17/2026 | Glossary UI | Glossary surface consumes this index. | Completed | Mayank
108 | Q-bank topic stats load wiring | Compute per-topic attempted/accuracy counts and surface filter-aware question availability. | Pending | Medium | 0 | 7/17/2026 | 7/19/2026 | Question bank topic picker UI | Picker reads stats from this loader. | Completed | Mayank
109 | Q-bank session create + question queue wiring | POST session start with topic/difficulty/length, server-build the question queue, return session id. | Pending | High | 0 | 7/18/2026 | 7/21/2026 | Question bank session runner UI | Runner bootstraps from this endpoint. | Completed | Mayank
110 | Q-bank answer-submit + explanation reveal wiring | POST per-question answer, return correctness + explanation + reference deep-link, advance pointer. | Pending | High | 0 | 7/19/2026 | 7/21/2026 | Question bank session runner UI | Runner posts each answer through this endpoint. | Completed | Mayank
111 | Q-bank session result + persist wiring | Compute final score, per-topic breakdown, flagged/wrong lists; persist attempt and update Q-bank coverage stats. | Pending | Medium | 0 | 7/20/2026 | 7/22/2026 | Question bank session results UI | Results page reads from this payload. | Completed | Mayank
112 | Mock paper metadata load wiring | Serve paper meta (title, format, Qs, time limit, pass mark) from course exam specs; gate by tier paper count. | Pending | Medium | 0 | 7/21/2026 | 7/23/2026 | Mock exam intro UI | Intro screen reads from this loader. | Completed | Mayank
113 | Mock runner timer + autosave + navigator wiring | Server-authoritative timer, debounced answer autosave, flag/visited bitmap for the navigator, resume after exit. | Pending | High | 0 | 7/22/2026 | 7/26/2026 | Mock exam runner UI (closed-book) | Runner reads/writes through this state engine. | Completed | Mayank
114 | Mock submit + scoring + lock wiring | Validate submission, score the paper, lock answers, mark attempt immutable in the audit log. | Pending | High | 0 | 7/24/2026 | 7/26/2026 | Mock exam submit-confirmation modal | Submit modal triggers this endpoint. | Completed | Mayank
115 | Mock result + readiness recompute wiring | Persist per-topic breakdown, surface review payload, recompute readiness score and tier-gate progress. | Pending | High | 0 | 7/25/2026 | 7/28/2026 | Mock exam results UI | Results page reads from this payload. | Completed | Mayank
116 | Readiness score composite engine | Compute the 0-100 composite from three inputs (mock attempts at pass mark, Q-bank coverage with anti-cherry-picking 50% floor per cluster, gap-report acknowledgements). Tier-aware weighting (Bronze 60/40, Silver 45/35/20, Gold 40/30/30). | Pending | Critical | 0 | 7/15/2026 | 7/22/2026 | Mock exam results UI | Recompute fires on every mock attempt, Q-bank session, and gap-report ack. | Completed | Mayank
117 | Readiness gate state machine + audit log | Implements active -> ready -> voucher_redeemed -> exam_scheduled -> exam_taken -> (passed ¦ failed) -> (closed ¦ refunded). Every transition stamped with timestamp, actor, and inputs for downstream claim defensibility. | Pending | Critical | 0 | 7/20/2026 | 7/28/2026 | Learner + enrollment data model | State lives on the enrollment record; transitions append to audit log. | Pending | Mayank
118 | Voucher inventory + awarding-body handoff | Voucher pool per awarding body (PeopleCert, PMI, APMG, Scrum Alliance, Scrum.org, DevOps Institute). Assignment on ready->voucher_redeemed, TTL/validity stamping, per-body reveal modal payload + booking-portal URL. | Pending | High | 0 | 7/22/2026 | 8/5/2026 | Course catalog data model | Each course family maps to one awarding-body adapter. | Pending | Mayank
119 | Awarding-body outcome webhook ingestion + verification queue | Inbound webhook from each awarding body where available (PeopleCert, PMI registry); manual-entry verification queue for bodies without an API. Marks exam_taken and records passed/failed with proof attachment. | Pending | High | 0 | 7/29/2026 | 8/12/2026 | Voucher inventory + awarding-body handoff | Outcome arrives keyed by the voucher issued in #118. | Pending | Mayank
120 | Money-back claim workflow + gate-honored audit check | Claim form ingestion (Gold only). Server-side verification that the readiness gate (#117) was honored at the moment of voucher redemption — no override means valid; override means auto-reject with referenced explanation. | Pending | Critical | 0 | 8/1/2026 | 8/14/2026 | Readiness gate state machine + audit log | Audit log is the only source-of-truth for the gate-honored check. | Pending | Mayank
121 | Refund processing integration | Payment-rail integration for approved claims (route through the same processor used in Stage 1 checkout for charge-back fidelity). Status timeline events: submitted -> verified -> approved -> refunded. | Pending | High | 0 | 8/5/2026 | 8/15/2026 | Money-back claim workflow + gate-honored audit check | Only approved claims hit the refund processor. | Pending | Mayank
122 | Transactional email pipeline | Templated outbound mail for: LMS welcome + activation, password reset, onboarding nudges, voucher-expiry warnings, claim-status updates, retake reminders, renewal-cycle nudges. ESP integration + suppression list + bounce handling. | Pending | High | 0 | 7/8/2026 | 7/20/2026 | Auth session + RBAC middleware wiring | Activation/reset flows depend on this pipeline. | Pending | Mayank
123 | Override request flow (early voucher redeem) | Support-routed override that lets a learner unlock the voucher before the gate passes. Hard confirmation modal text 'Redeeming early forfeits the money-back guarantee'. Override event is the audit-log entry that #120 rejects against. | Pending | Medium | 0 | 8/10/2026 | 8/14/2026 | Voucher inventory + awarding-body handoff | Override mints a voucher outside the normal gate path. | Pending | Mayank

## Instructions
BULK TASK UPLOAD — HOW TO USE THIS TEMPLATE
1. Open the "Tasks" sheet (first tab).
2. Replace the sample rows with your own. Keep the header row in row 1 unchanged.
3. Save the file as .xlsx (or export to .csv) and upload via "Bulk Upload Tasks" in the project page.
IMPORTANT
• Only the "Title" column is required. Every other column is optional.
• Dates can be MM/DD/YYYY (US) or YYYY-MM-DD. Excel date cells are also accepted.
• Progress must be a whole number between 0 and 100.
• If a row has any Dependency fields filled, "Dependency Task" must be set.
• "Dependency Owner" accepts an active user's full name OR a comma-separated list of names. See the Reference tab for the full list.
• Empty rows are skipped. Rows missing the Title will be flagged in the preview.
INSTRUCTIONS PER COLUMN
Field | Required? | What to enter | If left blank
A. Title | Yes | A short task name (preferably under 80 chars). This is how the row appears in the upload preview. | Row is skipped and shown as invalid in the preview.
B. Description | No | Free-text details / context. Newlines are preserved. | No description on the imported task.
C. Status | No | One of: Pending / In Progress / Completed (see Reference tab for synonyms). | Defaults to Pending.
D. Priority | No | One of: Low / Medium / High / Critical. | Defaults to Medium.
E. Progress | No | Whole number 0 to 100. | Treated as 0. Auto-set to 100 if Status = Completed.
F. Start Date | No | When work begins. MM/DD/YYYY or YYYY-MM-DD or an Excel date cell. | No start date set.
G. Due Date | No (rec.) | Deadline. Same date formats as Start Date. Recommended for reporting. | Task is un-dated; reports treat it as having no deadline.
H. Dependency Task | See note | Name of the upstream/blocking task. Required if ANY of I, J, or K below is filled. | No dependency recorded on the task.
I. Dependency Details | No | Why the dependency blocks. Free-text. Only meaningful if H is set. | No detail; the dependency exists but with no extra context.
J. Dependency Status | No | One of: Pending / In Progress / In Review / Completed / Blocked. | Defaults to Pending. Only meaningful if H is set.
K. Dependency Owner | No | Full name(s) of an active user. Single name or comma-separated for joint ownership. See Reference tab for the live list of valid names. | No owner attached. Unmatched names are flagged in the preview.
L. Final Comments | No | Wrap-up note added when the task closes. Often filled in when Status = Completed. | No closing note on the imported task.
NEED MORE DETAIL?
• The "Reference" tab lists every accepted value, synonym, and example for each column.
• Need a plaintext version? Use the "CSV" template from the same modal — same columns, no extra tabs.

## Reference
REFERENCE — Accepted values and examples for every column
Use this tab when filling in the Tasks sheet. Sections appear in the same column order.
─── A. TITLE (required, free text) ───
Guidance | Notes
Short | Aim for under 80 characters. Title is the row identifier in the preview.
Action verb | Start with a verb where natural — "Build homepage hero", "Refactor login flow".
Unique | Two rows can share a title, but unique titles make dependencies easier to reference.
Examples
Header design
Homepage hero animation
SEO audit fixes
─── B. DESCRIPTION (optional, free text) ───
Guidance | Notes
Multi-line | Newlines are preserved on import. Use them for sub-bullets or context.
Length | No hard cap, but the preview truncates very long values for readability.
Examples
Build the responsive site header with sticky navigation
Move all forms to react-hook-form + zod
─── C. STATUS (optional enum, defaults to "Pending") ───
Value | Notes / Synonyms accepted on import
Pending | Default. Synonyms: Not Started, To Do, Open, Backlog.
In Progress | Work is underway. Synonyms: WIP, In-Progress, Working, Doing.
Completed | Done. Synonyms: Done, Closed, Finished, Shipped.
─── D. PRIORITY (optional enum, defaults to "Medium") ───
Value | Notes
Low | Nice-to-have / low impact.
Medium | Default if left blank.
High | Important and time-sensitive.
Critical | Highest urgency — blocks releases or revenue.
─── E. PROGRESS (optional integer, 0–100) ───
Value | Notes
0 | Not started. Use with Status = Pending.
1 to 99 | In flight. Whole numbers only. Decimals are rounded down.
100 | Fully done. Auto-set if Status = Completed and Progress is blank.
Blank | Treated as 0.
─── F. START DATE (optional, date) ───
Format | Example
US slash | 6/15/2026
ISO | 2026-06-15
Excel date cell | Any cell formatted as a date in Excel works.
Blank | No start date set — the task can begin immediately.
Rule | Must be on or before Due Date if both are set.
─── G. DUE DATE (optional, date — recommended) ───
Format | Example
US slash | 6/30/2026
ISO | 2026-06-30
Excel date cell | Any cell formatted as a date in Excel works.
Blank | No deadline shown on the task row. Reporting will treat it as un-dated.
─── H. DEPENDENCY TASK (optional, free text) ───
Guidance | Notes
Format | Plain task name. Doesn't need to exactly match another row's Title.
When to use | Whenever this task is blocked or waiting on another piece of work.
Rule | If ANY of columns I, J, or K is filled, column H must also be filled.
Examples
Brand guidelines sign-off
API error contract
Hero copy approval
─── I. DEPENDENCY DETAILS (optional, free text) ───
Guidance | Notes
Purpose | Explain what you're waiting for and why it blocks.
Examples
Need final logo + colour tokens before final pass
Backend needs to standardise validation error payload
Awaiting final hero copy from content team
─── J. DEPENDENCY STATUS (optional enum) ───
Value | Notes
Pending | Hasn't started.
In Progress | Owner is working on it.
In Review | Awaiting review/sign-off.
Completed | Done — no longer blocking.
Blocked | The dependency itself is blocked.
─── K. DEPENDENCY OWNER (optional, matches an active user's full name) ───
Format | Notes
Single | One active user's full name — e.g. "Kiran R".
Multiple | Comma-separated for joint ownership — e.g. "Kiran R, Lokesh".
Match rule | Case-insensitive. Exact match preferred; startsWith and contains are used as fallbacks.
Unmatched | Names that don't match any active user are flagged in the preview so you can fix them before importing.
Active user names — accepted values
# | Full name
1 | Kiran R
2 | Lokesh
3 | Mayank
4 | NagaPrasanth
5 | Nageswara Rao
6 | Ranjith Kumar
7 | Somashekara
8 | Spandana HR
9 | Surya L
10 | Vaibhav
11 | Vamsi Krishna
12 | Venkataramana
13 | Vijay
14 | Vijay 2
15 | Vimala Nayuni
Tip | This list is generated live from the database at download time. Re-download the template if a new member joins.
─── L. FINAL COMMENTS (optional, free text) ───
Guidance | Notes
When to use | Wrap-up note. Often filled in when Status = Completed.
Examples
Done — all audit items addressed.
Awaiting brand sign-off; once approved, can wrap in a day.
Frontend pieces done; integration paused on backend contract.